## schedule
2022-01-01 | 3RD | 10H | 17TH | 24TH | 31ST
MON |  |  | Discussion with Atol re laser cutting and other concepts | Discussion with metal workshop for folding metal plates | Commence response in painting
TUE |  |  | Consider response in sculpture formate - who to contact and materrials | Send illsutartor files to Atol | Explore screen printing
WED |  |  | plan laser cutting / develop images | screen printing | Review tests / walk around london for imagery / materials
THU |  |  | laser cutting session mathew | laser cutting with Mathew
FRI |  |  | Source materials for further printing plates | Review tests / walk around london for imagery / materials
2022-02-01 | 1ST | 7TH | 14TH | 21ST | 28TH
MON | Develop folded mono prints | Make makets for sculpture elements | Review all realults from print tetsing and how they may work together | Send files to Atol for laser cutting / experiment with displaying fragment prints | Review schedule / use scanner in photography morning / screen printing on black paper and wood afternnon
TUE | Plan and prepare files for further laser cut plates | source tree for exhibition | Plan plates to be made
WED | Explore working with metal plates / screen printing | vacuum pack prints testing | Installation of selectioj of prints in basement
THU |  | screen printing | Screen printing | laser cutting with Mathew
FRI
2022-03-01 | 1ST | 7TH | 14TH | 21ST | 28TH
MON | Paint of canvas baord prints | Goldsmiths CCA visit - monuments / OHSPROJECTS | Tutorial with Nico / refelect on studio space following crit | Printmaking / test exhibitons | Conversation with Rebecca from Arbyte / contact Naomi - equipment for test exhibiton - TV, media player and lighting. Test exhibitions
TUE |  | Dissertation | Sketches
WED |  | Prepare for crit / dissertation tutorial | Digital drawings | Screen printing | Dissertation tutorial / screen printing afternoon
THU |  | Silent Crit | Gallery visits - Sadie Coles HQ and Whit Cube | Laser cutting | Meet Naomi in Photography / expose screen / Discusion with Mathew re cnc routing - plan sections to be routed. Photography workshop
FRI | Vacuum packing experiemnt with ink and paper | Blog and research | Review drawings / digital manipulation for screens | Re-work studio space and hang large digital prints - reflection. Go back to initial folded prints and use for hybrid prints - explore painting as surface for photocopying | Further explore photocopying work
Weekend | Document laser cut tests and print wooden pixel | Observe print fragments and document. Print perspex plate at home and test masked off painting
2022-04-01 | 1ST | 4TH | 11th | 18th | 25th
MON | Book digital camera for photograping work. Prepare final screen for 10m prints. Prepare for test exhibition | Set-up for test exhibiton and document |  |  | Reflect and document canvas prints
TUE | Hex code paint experiment |  | screen printing | Screen printing
WED | Hybrid prints and test lining paper | Screen printing - 10m prints | screen printing - print on canvas | Photocopying arrangements / expose last screen for final 10m roll and screen print more canvas | Plan canvas photocopy - arrange and photograph / arrange work in studio space, document and reflect. Screen printing final roll in the afternoon.
THU | Paint canvas for black prints for test exhibition | Screen printing - 10m prints |  |  | Screen printing
FRI | Mix paint B&Q | Screen printing - 10m prints / cnc routing - film machine |  |  | Painting - hybrid prints
2022-05-01 | 2ND | 9TH | 16TH
MON |  | Keep clear - final adjustments | Exibiton hang
TUE |  | Keep clear - final adjustments | Exibiton hang
WED | Hybrid prints / screen printing afternoon | Keep clear - final adjustments | Exibiton hang
THU | Screen and canvas final prints - paint mdf panels | Clear studios | Exibiton hang
FRI | PRINTS TO BE FINISHED | Prepare exhibiton spaces

## budget
Materials | Production | Cost | unit price | total
Lining paper x3 10m rolls | for screen printing | 4.99 | 4.99 |  | Anaglypta 1400 grade 10m lining papar 0.53 x 10m
Printmaking paper | Printing | 200
Perspex sheets | Metal work | tbc
Mountboard | Canvas | 25
Metal sheets | Delivery | tbc
Metal plates - zinc and copper |  | tbc
Canvas |  | 100 | 10 |  | 60 x 80cm
Plywood sheets |  | 0
Oil paint |  | 50
Acrylic paint |  | 50
Marker pens |  | 10
Found materials |  | 0
Tree brances and logs |  | 0
Hoover |  | 0
Vacuum packing bags |  | 100
Foamboard |  | 10
MDF sheets x3 | CNC router | 60
mini gloss emulsion roller set x4 |  | 3.99
Acrylic paint for mdf plates |  |  | 10.99
white spirit |  | 2.99
a2 black 110g sketching paper |  | 2.7
canvsas panel triple pack |  | 11
canvas 4pk |  | 10
Black cloth tape |  | 3.68
seawhite sq |  | 5
Total |  | 649.35